## Project schedule
| Project SPYN | [5 empty] | Project start: | [7 empty] | 2023-09-26
| Tyler Nguyen | Project lead |  |  |  |  | Display week: | [7 empty] | 1
| SIMPLE GANTT CHART by Vertex42.com | [5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | [5 empty] | 2023-09-25 | [6 empty] | 2023-10-02 | [6 empty] | 2023-10-09 | [6 empty] | 2023-10-16 | [6 empty] | 2023-10-23 | [6 empty] | 2023-10-30 | [6 empty] | 2023-11-06 | [6 empty] | 2023-11-13
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2023-09-25 to 2023-11-19
 | time axis 2023-09-25 to 2023-11-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Milestone 1 - Getting Familiar with Connecting to EV
| Get Familiar With EV Kit | Tyler Nguyen |  | 2023-09-26 | 2023-09-29 | 4
| Decide on the design of the Car | Puneet Kaur |  | 2023-09-26 | 2023-09-29 | 4
| Use Matlab to connect to EV | Advait Yadav |  | 2023-09-29 | 2023-10-03 | 5
| Learn how to Utilize the motors of the Kit | Aarsh Duhlani |  | 2023-10-03 | 2023-10-05 | 3
| Make inputs to move EV | Brandon Prior |  | 2023-10-05 | 2023-10-07 | 3
Milestone 2 - Sensor Calibration
| Get Familiar with Sound Sensor | Advait Yadav |  | 2023-10-06 | 2023-10-10 | 5
| Get famliar with Color Sensor | Tyler Nguyen |  | 2023-10-06 | 2023-10-11 | 6
| Figure Out How to Pick Up Guy | Puneet Kaur |  | 2023-10-11 | 2023-10-14 | 4
| Integrate Color Sensor Into Car | Aarsh Duhlani |  | 2023-10-11 | 2023-10-13 | 3
| Integrate Sound Sensor Into Car | Brandon Prior |  | 2023-10-11 | 2023-10-14 | 4
Milestone 3 - Testing The Car
| Make sure the Car Doesn't Hurt Guy | Puneet Kaur |  | 2023-10-11 | 2023-10-16 | 6
| Ensure that the Car Doesn't Crash | Tyler Nguyen |  | 2023-10-11 | 2023-10-16 | 6
| Figure out how to Navigate The Car Around the Maze | Aarsh Duhlani |  | 2023-10-11 | 2023-10-16 | 6
| Work on Assignments on Canvas | Brandon Prior |  | 2023-10-16 | 2023-10-20 | 5
| Testing and validation | Advait Yadav |  | 2023-10-16 | 2023-10-20 | 5
Milestone 4 - Final Steps
| Demonstrate Car With Instructor | Brandon Prior |  | 2023-10-20 | 2023-10-23 | 4
| Configure Car For Race | Tyler Nguyen |  | 2023-10-23 | 2023-10-27 | 5
| Evaluate Progress | Advait Yadav |  | 2023-10-28 | 2023-10-31 | 4
| Evaluate Peers | Aarsh Duhlani |  | 2023-10-25 | 2023-10-28 | 4
| Final Implementation | Puneet Kaur |  | 2023-10-27 | 2023-11-01 | 6
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]
Week 2 = [Week 2, row below]
Week 3 = [Week 3, row below]
Week 4 = [Week 4, row below]
Week 5 = [Week 5, row below]
Week 6 = [Week 6, row below]
Week 7 = [Week 7, row below]
Week 8 = [Week 8, row below]

## About
SIMPLE GANTT CHART by Vertex42.com
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.